## Slide 1: Developing a QI Charter

## Slide 2: What is a QI Project charter
Roadmap of a QI project
  Document that structures a QI project
Helps teams visualize a shared goal
Outlines the “WHAT” “WHY” “HOW”
Communication tool across stakeholders
Iterative process

## Slide 3: Outline: Section I
INTRODUCTORY
  Team members
  Sponsor: Lillian Wanyama (Sub-county Public Health Nurse)
  Project Title:
    Improving Maternal Child Health Outcomes in Cherangany
  Project start date: 25th December 2021
  Project end date: 30th July 2022
  Last revised: xxxxxxxxxxx
Names | Designation | Role in QIT/WIT
Okemwa Osundwa | N.O In charge | Team lead
Atoya Alur | Clinical officer | Member
Menge Dusto | HRIO | Secretary

## Slide 4: Outline: Section II
AIM: What are we trying to accomplish?
  Problem statement
    Global picture
      (lit review, Africa/Kenya/Trans Nzoia?/Sub-county/Facility)
    Rationale/Justification
    Target population
    Expected outcomes
  AIM Statement

## Slide 5: Outline: Section II
2. MEASUREMENT: How will we know a change is an improvement?
Outcome measures
  Linked to your AIM
    Numerator – Define
    Denominator - Define
Process measures
  Linked to activities
    Numerator – Define
    Denominator - Define
Balancing measures
  Unwanted/anticipated negative effects of your project

## Slide 6: Outline: Section III
CHANGE: What changes will lead to an improvement?
  Initial Activities
  Changes
    Insert drivers diagram
  Key stakeholders – Those who have a stake in the process
  Barriers – Outside your control
  Mitigation strategies – how will we solve the barriers
Activity | Timeline | Responsible person
Train/CME staff on QI | 27th -31st October 2021 | Faith
Form a QIT/WIT | 2nd September 2021 | xxxx
Develop a QI charter | 5th September 2021 | xxxxxx

## Slide 7: section III
4. Sign Off
Community Rep
Sponsor
Ownership
Community participation – Other stakeholders buy in

## Slide 8: GROUP WORK
Team develop a QI charter for the QI project they have been working on since Day 1 of the training.

## Slide 9
THANK YOU
info@ampathkenya.org | www.ampathkenya.org | @ampathkenya